## Project Planner
Nutrient Analyzer
[5 empty] | Period Highlight | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Activity No. and Name | Plan (in days) Start | Plan(in days) Duration | Actual(in days) Start | Actual Duration(in days) | Percent Complete | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Project Planning | 1 | 3 | 1 | 3 | 100%
1.1 Scheduling initial meetings | 1 | 1 | 1 | 1 | 100%
1.2 Identify Stakeholders | 2 | 1 | 2 | 1 | 100%
1.3 Project team assembly | 3 | 1 | 3 | 1 | 100%
2. Analysis Tasks | 4 | 3 | 4 | 3 | 100%
2.1 Meeting to clarify project specifications | 4 | 1 | 4 | 1 | 100%
2.2 User activity modelling | 5 | 2 | 5 | 2 | 100%
3. Design Tasks | 7 | 5 | 7 | 5 | 100%
3.1 Designing the GUI | 7 | 3 | 7 | 3 | 100%
3.2 Database Design & Integration | 9 | 3 | 9 | 3 | 100%
4. Build Tasks | 11 | 9 | 11 | 9 | 100%
4.1 Developing the application interface | 11 | 3 | 11 | 3 | 100%
4.2 Features implementation | 13 | 4 | 13 | 4 | 100%
4.3 Integrate application interface,subsystem and database | 17 | 3 | 17 | 3 | 100%
5. Testing | 20 | 6 | 20 | 6 | 100%
5.1 Perform Unit Testing | 20 | 2 | 20 | 2 | 100%
5.2 Perform Statement Coverage Testing | 22 | 2 | 22 | 2 | 100%
5.3 Perform Branch Coverage Testing | 24 | 2 | 24 | 2 | 100%
6. Documentation and Final Reporting | 26 | 2 | 26 | 2 | 100%
6.1 Final Performance Review | 26 | 1 | 26 | 1 | 100%
6.2 Final Reporting | 27 | 1 | 27 | 1 | 100%
Activity 24 |  |  |  |  | 0%